## Sheet1
Section #: | 2023-04-01
Team Name: | TeraBITE
Name | Assigned Tasks | Total # of Planned Hours | When is it due? | Completion Status | Total # of Actual Hours Worked | Passed testing? | Remarks
Example | #20, #26 | 5 | #20: 12pm, 9/25 #26: 5pm, 9/25 | #20: 90191fb1, 11pm, 9/24 #26: 66c23b39, 8pm, 9/25 | 7 | #20: Yes, passed testcase1 #26: Partially passed Testcase2 | None
Jonathan Camarena | #ADAPTEDS-82, #ADAPTEDS-81 | 4 | #82,#81 11:59p 11/12 | #81: 7f3fe75, 11/11 | 3 |  | did not get to #82, but started it.
Casey Paras | #ADAPTEDS-46,#ADAPTEDS-48, #ADAPTEDS-22 | 5 | #46: 11/12 | #46: f965c2f | 5 |  | did not complete 48 &22
David Castrejon | #ADAPTEDS-50 | 4 | #50: 11/12 | #50: 8f067f8 | 4
Blake Danz | #ADAPTEDS-45 | 4 | #45: 6:00 p.m., 11/12 |  | 10 | #45 Did not complete task | It took some time for our backend team to implement a database and I need to do more research on email sending best practices
Danny Zhou | #ADAPTEDS-77 | 4 | #77: 6:00 p.m., 11/12 | #24: 8ef1eec 9pm, 11/12 | 16
Joshua Cupler | #ADAPTEDS-78 | 4 | #78: 600 p.m. 11/12 | ??? | 6 |  | Turns out #77 exceded story scope and partially encompsed this story. Need to go through impl, figure out what's been impl and what's left to do
Amir Talakoob | #ADAPTEDS-49 | 4 | #49: 6:00 p.m., 11/12 | #49: 12e0781 | 8 | Partially passed, did not pass the confirmed password test, rest of the tests were passed | Refer to task #89 for more information
Jeff Huang | #ADAPTEDS-51 | 4 | #51: 6:00 p.m., 11/12 | #51: 9e9e683 | 6 | Did not complete. Proof of concept, but no project specific version | Backend database was blocked for part of sprint
Ahmed Taeha | #ADAPTEDS-47 | 4 | #47 11/12 | n/a |  |  | Did not complete